## Notes
The information described in this tab "Notes" are intended only to assist you in creating this document. This tab should be deleted before release of the record based on this Form. The procedure described in the Procedure Corrective and Preventive Actions should be followed. The version history below applies to the template and not to the resulting document. Clean up the table as needed and use it for your document control purposes.
Version | Date of validity | Author | Description of change
1 | 2022-06-01 | Célia Cruz | First version

## CAPA List
[LOGO] |  |  | List Corrective and Preventive Actions (LST-CP-01)
| Date of last update: | YYYY-MM-DD
CAPA ID | Source (e.g. Audit ID, Customer Complaint, Management Review) | Observed by | Registration by | Statement / Title | Determination date [YYYY-MM-DD] | Is customer follow-up needed? | CAPA? | Root cause analysis | Action decision (improvement, correction, corrective action, preventive action) | Action | Planned implementation of action(s) [YYYY-MM-DD] | Responsible person for implementation | Action(s) implemented [YYYY-MM-DD] | Reference to record for implementation | Effectiveness evaluation | Results of effectiveness evaluation | Effectiveness check completed at [YYYY-MM-DD] | Date closed [YYYY-MM-DD] | Comments
1 | Usability feedback |  |  | No contact details provided as part of product information | 2022-06-01 |  | CAPA | Loss of information during development |  | New product release incl. contact details; update development process | 2022-06-05 |  | YYYY-MM-DD |  | Number of future complaints related to this issue; review of technical information by Notified Body for completeness
[5 empty] | YYYY-MM-DD |  | No CAPA |  |  |  | YYYY-MM-DD |  | YYYY-MM-DD

## Main Causes Example
Main causes
1. Processes, procedures, instructions
¡ procedure not followed
¡ Poor procedure
¡ Obsolete document
2. Human errors and personal performance
¡ Excessive workload
¡ Defective working environment
¡ Poor attention
¡ Lack of skills
¡ Lack of discipline
¡ Personal problems
3. Training
¡ Lack of training
¡ Training not effective
4. Management factors
¡ communication problem
¡ Poor control
¡ Lack of staff
5. Suppliers
¡ supplier problem
¡ Poor incoming inspection
¡ Poor procurement specification
6. Product and Tools
¡ Defective product
¡ Incorrect specification
¡ Defective labeling / instructions for use
¡ Defective packaging
¡ Inadequate storage
¡ Defective service
¡ Abuse / Abnormal use
¡ Problems with shipping
¡ Defective test
¡ Inadequate installation / validation

## Drop Down
CAPA
No CAPA